## Project Summary
Project Name
Project Lead
Start Date
Estimated End Date
| Assumptions |  | Risks |  | Issues |  | Changes
| Total # Raised |  | Total # Open |  | Total # Open |  | Total # Raised
| 1 | Critical | 1 | Critical | 1 | Critical | 1 | Critical
| 1 | High | 1 | High | 1 | High | 1 | High
| 1 | Medium | 1 | Medium | 1 | Medium | 1 | Medium
| 1 | Low | 2 | Low | 1 | Low | 1 | Low

## Assumptions
ID | Title | Description | Implication Description (if proven false) | Implication Area | Assumption / Constraint | Stakeholders Involved | Criticality | Status | Planned Actions | Last Update Date | Owner
1 |  | There is an assumption that …. |  | Schedule | Assumption |  | Critical | New |  | 2012-01-02
2 |  | There is an assumption that …. |  | Hours | Constraint |  | High | Active
3 |  | There is an assumption that …. |  | Budget |  |  | Medium | Upheld
4 |  | There is an assumption that …. |  | Technical |  |  | Low | FALSE
5 |  | There is an assumption that …. |  | Resources
6 |  | There is an assumption that …. |  | Cust Success
7 |  | There is an assumption that …. |  | Legal
Note on A3: Unique identifier for the Assumption or Constraint
Note on B3: Brief name to easily reference the Assumption or Constraint in discussions and reporting. This IS NOT the complete description.
Note on C3: Describe the Assumption or Constraint. This should include: - How the Assumption came about (e.g. It is assumed that the Interface for Get_Customer_Details will be ready by end of Sprint 4.) - Background events that contributed to the making of the Assumption or Constraint (e.g. This engagement involves 4 Interfaces being developed by the Customer.)
Note on D3: Describe the impact that the Assumption or Constraint will have if proven false. This should include: - Area of impact: Scope (technical), Schedule (phase, sprint, project), Budget (hours, expenses), Resources, Customer Success - How will the plans for the area of impact alter? (e.g. number of sprints required to deliver scope cannot be achieved)
Note on E3: Choose the primary area of impact from the drop down list. In most cases, more than one area of the engagement will be affected, therefore choose the area that will be impacted greatest. Schedule - number of sprints or end date will not be met Hours - effort to deliver engagement will be compromised; this could be either due to additional staff or an extension in time frame Budget - the cost to deliver the engagement will be compromised; this could be either external or internal costs Technical - the technical solution could be compromised Resources - the engagement team could be compromised either through the skills, time, allocation, etc. Customer Success- the customer satisfaction could be compromised Legal - license, service, SOW, or any other legal factor that supports the engagement could be compromised
Note on F3: Assumptions and Constraints are similar though different. Constraint - an immoveable barrier or restriction that the engagement must plan and work within the boundaries Assumption - anything that is perceived to be true in the planning and delivery of the project, although there may be no basis for the perception Choose the correct entry from the drop down list.
Note on G3: List the names of the primary stakeholders who have been involved in identifying, agreeing, or prescribing the Assumption or Constraint.
Note on H3: Choose the correct Criticality for the Assumption or Constraint. Valid options include the following: Critical: This will stop project progress if the Assumption is proven true or the Constraint boundary is not met. High: This will have a significant affect on the project and/or will require significant resources to resolve if the Assumption is proven true or the Constraint boundary is not met. Medium: This will have a material affect on the project and/or will require some resources to resolve if the Assumption is proven true or the Constraint boundary is not met. Low: This is expected to have a moderate effect on the project, but will NOT require resources to resolve if the Assumption is proven true or the Constraint boundary is not met.
Note on J3: DOCUMENT THE HISTORY and ACTIVITIES COMPLETED FOR THIS ASSUMPTION OR CONSTRAINT in this column.
Note on K3: The date when this Assumption or Constraint was last discussed and/or had action performed against it.
Note on L3: The name of the person responsible to action the next activity for the Assumption or Constraint.

## Risks
ID | Risk Name | Description (If <this happens>…) (then, <this will happen>...) | Score |  |  |  | Treatment | Status | Mitigation Strategy/ Actions to Take | Last Update Date | Update Status | Owner
|  |  | IMPACT 1=Low 5=High | LIKELIHOOD 1=Low 5=High | SCORE | CRITICALITY
1 | Excessive additional scope | If excessive additional scope is added to the project, then the backlog may grow to an unachieveable amount of user stories for the schedule deadlines and budget. | 5 | 5 | 25 | Critical | Avoid | Not Mitigated | The EL will manage the backlog reporting on a weekly basis each sprint, phase, and the overall project to estimate to complete for time and dollars. | 2015-10-28 | Review the backlog to ensure additional scope (effort) beyond the current teams capacity is NOT added. | Perfect Pete
2 |  | (If <this happens>…) (then, <this will happen>...) | 4 | 2 | 18 | High | Accept | Being Managed
3 |  | (If <this happens>…) (then, <this will happen>...) | 3 | 3 | 14 | Medium | Reduce | Fully Mitigated
4 |  | (If <this happens>…) (then, <this will happen>...) | 2 | 2 | 8 | Low | Transfer
5 |  | (If <this happens>…) (then, <this will happen>...) | 1 | 5 | 7 | Low
6 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
7 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
8 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
9 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
10 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
11 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
12 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
13 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
14 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
15 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
16 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
17 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
18 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
19 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
20 |  | (If <this happens>…) (then, <this will happen>...) |  |  | 0
Note on A3: Unique identifier for the Risk
Note on B3: Brief name to easily reference the Risk in discussions and reporting. This IS NOT the complete description.
Note on C3: Describe the risk. This can include background events, further details on areas of impact, etc. HOWEVER, The risk statement should clearly state potential Cause and the Effect, if the risk becomes true. An easy way to write the statement is, "If ... happens, then ... will happen." This helps to clearly describe a risk.
Note on D3: The Score is the science to measuring the importance of a risk. This allows focus to be given to Risks that are most likely and will cause the most impact to an Engagement if the Risk were to become true. Columns D & E should be agreed during the Risk Elicitation Meeting. Coolumns F & G are calculated using embedded formulas.
Note on H3: Risk treatment categories are: Avoid - steps will be takene so that this risk does not become true Accept - no steps will be taken. The engagement accepts that the risk may become true, however either the likelihood is low, the cost to mitigate too high, or another factor that requires the risk to be accepted Reduce - steps will be taken to minimise the impact should the risk become true Transfer - the risk will be given to an interdependent party to resolve; this engagement does not have the authority, expertise, or other limiting factor to mitigate the risk
Note on I3: Choose the current state of the Risk Not Mitigated - The risk has been accepted or no activities to mitigate have yet begun. The risk is closed and will no longer be worked on. This status should be used when a Risk becomes an Issue and is transferred into the Issues Log for resolution. Being Managed - The risk is actively being worked on. Work that might be in progress is designing a solution, developing the solution, getting more resources, etc. Fully Mitigated - The risk is no longer considered an active threat and can be closed with or without resolution. No further activity will take place.
Note on J3: Describe the risk strategy and/or activities required to mitigate this risk. Ensure that the activities directly link to a risk treatment category. If the risk is to be Accepted, this cell should contain information on who has approved that acceptance. The risk acceptance should also be recorded in the Decisions Log. Once a risk is accepted, the Status (column I) can be updated to Not Mitigated
Note on K3: Enter the date when this Risk was last discussed and/or had action performed against it.
Note on L3: Some Risks can be large and will require a mitigation strategy to mitigate The best way to approach this is to break the strategy into smaller activities, working each action until the Risk is mitigated. This may stretch over a long period of time. This will require regular monitoring to keep the mitigation strategy on track and ensure the risk does not become true. In this column, document updates from the owner and team on a regular basis. Recommendation is every 1-2 weeks, until the Risk is mitigated.
Note on M3: The name of the person responsible to action the next aqctivity in the Mitigation Strategy or Update Status.
Note on D4: Guidline to assigning Impact Values Score 5 Outcome is risk were proved true - Project will not delivery to goals or objectives Implication - Project Failure Stakeholder/Customer Impact - Beyond repair Score 4 Outcome is risk were proved true - Significant areas impacted; Significant descoping required Implication - Project goals under threat Stakeholder/Customer Impact - Severe damage Score 3 Outcome is risk were proved true - Some areas will not deliver as planned; descoping required Implication - Significant impact Stakeholder/Customer Impact - Considerable damage Score 2 Outcome is risk were proved true - Changes beyond project tolerances or contingency Implication - Measurable but not destructive impact Stakeholder/Customer Impact - Some damage Score 1 Outcome is risk were proved true - Minor changes to deliverables Implication - Absorbable within project tolerances Stakeholder/Customer Impact - Changed; not damaged
Note on E4: Guideline to assigning Liklihood values Score 5 >75% - Almost certain without intervention Score 4 50-75% - High liklihood; easily foreseeable event Score 3 25-50% - Probable; may have occurred in similar projects Score 2 5-25% - Possible with a improbable sequence of events Score 1 Les than 5% - An unlikely or freak event
Note on G4: CRITICALITY will be determined through a best practice formula. Recommended immediate actions to take, based on Criticality score are: Critical: Risk will stop project progress if not appropriately mitigated. Escalate immediately to the controlling group or executive board. Take immediate action to mitigate. High: Risk will have a significant impact on the project if not appropriately mitigated. Inform the controlling group or executive board. Put mitigation strategy or plan into action. Medium: Risk will have a material affect on the project. Manage risk and escalate in normal reporting. Watch carefully for any changes. Low: Risk is expected to have a moderate effect on the project. Track risk
Note on J5: Goslin, Hope: Confused as to how thi should read… How about "The EL will manage the backlog reporting on a weely basis (each sprint, phase, and the overall project) in order to estimate the time and dollars.

## Issues
ID | Issue Name | Description | Impact Description | Criticality | Status | Resolution Strategy/ Actions to Take/Updates | Last Update Date | Owner
1 |  |  |  | Critical | New
2 |  |  |  | High | Active
3 |  |  |  | Medium | Resolved
4 |  |  |  | Low | Closed/Unresolved
Note on A3: Unique identifier for the Issue
Note on B3: Brief name to easily reference the Issue in discussions and reporting. This IS NOT the complete description.
Note on C3: Describe the Issue. This should include: - If this Issue was the result of a Risk becoming true, the Risk information should be included - Background events that contributed to the Issue This cell should describe 'What' happened and 'How' or 'Why' it happened.
Note on D3: Describe the impact that the issue has made. This should include: - Area of impact: Scope (technical), Schedule (phase, sprint, project), Budget (hours, expenses), Resources, Customer Success - How will the plans for the area of impact alter?
Note on E3: Choose the most appropraite score for the priority of the issue using the drop down box. Valid options include the following: Critical: Issue will stop project progress if not resolved. Escalate immediately to the controlling group or executive board. Control at source. High: Issue will have a significant affect on the project in terms of customer success, budget, schedule, quality or scope, and/or will require significant resources to resolve. Manage immediately. Inform the controlling group or executive board. Please the issue strategy and actions. Medium: Issue will have a material affect on the project in terms of customer success, budget, schedule, quality or scope, and/or will require some resources to resolve. Manage issue and escalate in normal reporting. Watch carefully for change in impact. Low: Issue is expected to have a moderate effect on the project, but will not require resources to resolve. Track issue.
Note on F3: Choose the current state of the Issue. New A new Issue has been raised, however no activity has commenced to resolve the Issue. Active The Issue is actively being worked on. Resolved The Issue is considered to be fully and successfully resolved. Closed/Unresolved: The Issue is no longer being worked on, however the Issue was not resolved successfully.
Note on G3: THIS COLUMN SHOULD TRACK THE HISTORY OF RESOLVING THE ISSUE. Describe the strategy and/or activities required to resolve this Issue. Some Issues can be large and will require a strategy to resolve. The best way to approach this is to break the strategy into smaller activities, completing each action until the Issue is resolved. This may stretch over a long period of time. This will require regular monitoring to keep the resolution activites on track to ensure the Issue is resolved. Document updates from the owne and team in this column, on a regular basis. Recommendation is every 1-2 weeks, until the Issue is resolved.
Note on H3: The date when this Issue was last discussed and/or had action performed against it.
Note on I3: The name of the person responsible to action the next activity in the Mitigation Strategy or Update Status.

## Change_Log
ID | Current Status | Date Identified | Requestor Name | Type of Change | Business Priority | Business Impact | Description | Backlog Impact | Resource/ Team Impact | Hours | Project Schedule Impact | Project Budget Impact | Approval Date | Approval Type
1 | New | 2006-01-01 | Perfect Pete | New Requirement | Emergency | Critical | There were inconsistencies within the party/feature use cases that were discovered during development and BA review. The updates outlined below are required to be made to the use case and are reflected in each place where data elements are mentioned. Changes must be reviewed and made to the following sections of each use case where appropriate: Flow of Events, Data Capture spreadsheet, Business Rules, and Application Error Messages. | Use Cases UC 06 – Insured Driver Details UC 08 – Third Party Customer Driver Details UC 11 – Passenger Details UC 12 – Capture Motorcyclist Details [To be removed] UC 13 – Capture Cyclist Details [To be removed] UC 14 – Capture Pedestrian Details UC 15 – Capture Witness Details UC 16 – Capture Misc. Property Damage Details UC 17 – Capture Glass Claim Details UC 18 – Capture Contact Details Update Categories Flow of Events Data Capture spreadsheet Business Rules Application Error Messages | + .5 UX 3 sprints | +25 | 4 week delay | + $30,000 | 2017-01-15 | Threshold
2 | Drafted |  |  | Requirement Change | Urgent | High | [7 empty] | Owner
3 | Submitted |  |  | Design Change | Routine | Medium | [7 empty] | Sponsor
4 | Re-Submitted |  |  | Other |  | Low | [7 empty] | CCB
5 | Follow-up Required | [12 empty] | Rejected
6 | Withdrawn
7 | Completed
8 | Deferred
9
10
11
12
13
14
15
Note on A3: A unique number used to uniquely identify the change. Ensure the number here is the same as the number on the Change Request Form.
Note on B3: The current status New - CR has been assigned. Drafted - CR has been documented and is ready for Project Team Review. Submitted - CR has been submitted to the Change Control Board; awaiting CCB review. Re-Submitted - CR has been re-submitted to the CCB after follow-up. Follow-up Required - CCB could not fully evaluate CR; further information needed from the CR Assignee. Approved - The CCB decided to implement the request. Withdrawn - A decision has been made to withdraw the CR. Completed - An approved CR has been processed and the request is now completed. Deferred - The CCB decided to implement the request change during a later phase of the project. Rejected - The CCB decided not to implement the requested change.
Note on C3: The date the change was identified.
Note on D3: The name of the person requesting the change.
Note on E3: Choose the type of change from the list.
Note on F3: Choose the urgency in which this change must be completed Emergency: Change will stop project progress and critically impact the Business if not approved and actioned immediately. Urgent: Change will have a significant affect to the project goals and highly impact the Business if not approved and actioned quickly. Routine: Change will have material effect to the project goals and moderately impact the Business if not approved and actioned.
Note on G3: Choose the impact to the Business if this change is not approved. Critical: Change will stop project progress if not approved and actioned within current sprint cycle. High: Change will have a significant affect to the project goals if not approved and actioned quickly. Medium: Change will have material effect to the project goals if not approved and actioned. Low: Change may impact the project goals and would be 'nice to have'.
Note on H3: Provide a brief description of the change. The Change Request Form contains all the details so the Change_Log should not be a duplicate. However a description that will set each Change uniquely apart should be provided. The reason 'why' the Change is needed will usually give the right level of detail.
Note on I3: List the impact that this Change will have to the backlog if approved. Has the backlog grown? By how many user stories? Will the additional items add a significant load to the backlog? This is where the overall impact of the Change to the project is explained.
Note on J3: List and quanitfy the impact to the project team. This could be additional resources, special skills required, a reduction in resources, etc.
Note on K3: List the number of hours required to complete this Change. A reduction in hours is also acceptable.
Note on L3: List additional or reduction in time to the OVERALL project as a result of this Change.
Note on N3: The date that the Change was approved.
Note on O3: Choose the type of approval this Change requires. All changes should be logged, however not all changes will be reviewed by CCB (Change Control Board). Threshold: Choose this when approval is not required because the Change is within the EL/PL empowered threshold Owner: Choose this when the approval has been given by the Project Owner Sponsor: Choose this when the approval has been given by the Project Sponsor CCB: Choose this when the approval has been given by the Change Control Board Rejected: Choose this when the Change has been submitted, however the Change was not approved
Note on M4: Insert the dollar value that Pega will be responsible for, for this change

## Communications_Plan
WHAT |  | HOW | WHEN |  | WHO |  |  | Current Status | CONTENT |  |  | Special Considerations
Comms Name | Category | Delivery Method | Planned Delivery Date | Recurrence/ Dist Cycle | Writer | Sign Off | Sender |  | Audience | Objective | Key Messages
Kick Off Meeting | Awareness | Email |  | Weekly x 6
Scope Session | Pre-launch | WebEx
Project Status Update | Escalation | Webinar
| Education | Roadshow
Note on I3: The current status New The Coomunication has just been identified. At the start of an egagement while in planning, most likely all the communcations will be in this state. Active: The Communication is actively being worked on. Pending: The Communication is waiting for the date that work will commence on its creation and release. Released: The Communiation has been successfully released. No further work is required. Withdrawn: The Communication has been withdrawn. For reasons it is deemed no longer required. Use this status instead of simply removing the row. This creates an audit trail.
Note on M3: Describe any special conditions. This could apply to either the creation or the release of the Communciation.
Note on A4: Brief name to easily reference the Communication item in discussions and reporting. This IS NOT the complete description.
Note on B4: The Category is the type of communication that the item is. Type helps define the urgency, the type of delivery mechanism, the timing for when it is needed, and possibly any type of special messaging (e.g. Education will typically have more instruction than an Awareness item)
Note on C4: The mechanism that will be used to deliver the message (e.g. Social Media, Email, Report, etc.)
Note on D4: Enter the date that the engagement plans for the Communication to be released. If this is a recurring Communication, initially use the first date, then update with a new date for each recurrence.
Note on E4: Enter the cycle that this communication will reoccur and how many times that is expected during the engagement (e.g. Weekly x 6; every Tuesday; prior to each go live)
Note on F4: Name of the person who will write the Communication
Note on G4: Name of person who will perform Communication review and who certifies that it is correct, has complied with Pega standards, and will meet the Objective (column J).
Note on H4: The name of the person who will be releasing the Communication.
Note on J4: List who will receive the Communication. This can be groups of people, organisations, and/or indiividual people.
Note on K4: In a simple statement, describe what the communication must achieve in order for it to be considered successful.
Note on L4: Describe the message that the Communication must convey. This is not intended to be a word for word of the Communication. It is the 'raw' message without any 'word wizardry'. (e.g. send email to convey successful go live)

## Decisions_Log
Decision ID | Decision Date | Decision Description | Who Made Decision | Location When Made | Impact Description (what is going to change) | Background to Decision
Note on A3: A unique number used to uniquely identify this Decision
Note on B3: The date that the Decision was made
Note on C3: Provide a description of the Decision.
Note on D3: Provide the name of the person who made the Decision. This could be either an internal or external decision maker. If it was a group concensus, include the names of all individuals or the meeting name, date, and time.
Note on E3: Provide the Location where the decision was made. This is important because several project decisions are made instanteously. This keeps the project moving ahead and should not be discouraged. Cateloguing these Decisions helps bring together the formal with the informal.
Note on F3: Describe the impact to the project that this Decision will have. Consider all project key performance areas - Scope, Schedule, Budget, Resources, Technical Solution, Customer Success, etc.
Note on G3: Provide the background story to why this Decision was required.

## Reference_Sheet (hidden)
RISK REFERENCE MATRIX
Likelihood
| 0 | 1 | 2 | 3 | 4 | 5
Impact | 1 | 1 | 3 | 4 | 5 | 7
| 2 | 2 | 8 | 9 | 10 | 11
| 3 | 6 | 13 | 14 | 15 | 16
| 4 | 12 | 18 | 19 | 20 | 21
| 5 | 17 | 22 | 23 | 24 | 25