## Sheet1
Go / No-Go Checklist
This document is an example go/no go check list to help determine if you are ready to put your journey live. This can be customized to meet the needs or your project/customer.
# | Checklist | Completed | Mitigation (if not completed)
Technology
1 | Clean data conversion has been performed and verified
2 | No Severity 1 errors persist
3 | All Severity 2 errors that persist have workarounds acceptable to the the business or are on a trajectory for correction and regression testing within a manageable time period agreed to with the business
4 | All system interfaces have been tested and certified
5 | Performance Tests are complete and results signed off by the business as acceptable
6 | Penetration Tests have been completed successfully
7 | All test signed off by the business (E2E, UAT, Performance, Security, Distribution, Industry specific).
8 | All necessary hardware and software are in place and running current versions of the firmware/operating system
People
1 | Business partners have confirmed their willingness and ability to support the go-live date
2 | The CIO and managers of any impacted user departments have agreed in writing to any exceptions to items on this list
3 | Coordinate with partners, client, and any other stakeholders
4 | All required users have been setup and are ready for access once live
5 | All go live signatories identified and have provided approval for go live
6 | Floor walkers for call centres etc organised to support go live
7 | Identify cutover resources
8 | Data and Testers for Smoke Tests identified
9 | Resources (primary and back up) secured for the deployment time
10 | Building access secured for smoke testers (if out of hours)
Process
1 | Define cutover strategy
2 | Create a backup/restore process
3 | Complete or plan for user-training
4 | Identify a fallback plan if the cutover needs to be aborted
5 | Create validation tests to confirm cutover was successful
6 | Deployment Runsheet of steps, timings and owners created
7 | Dress rehearsal of deployment completed successfully
8 | Outage agreed with Operations (eg call centre downtime)
9 | Communication plan and recipients agreed
10 | CLOUD: Pega Diagnostic Cloud training complete and monitoring planned for
11 | ON PREM: All infrastructure is up to date with the current organisational IT compliance standards
Adoption
1 | Daily calls planned for post deployment to discuss issues/defects raised organised
2 | Updated desk procedures are created and ready for distribution to all affected users
3 | Help desk documentation for the new system is ready
4 | Schedule the project retrospective
5 | Plan for post-production support
6 | Identify who will be taking over support
7 | Schedule handoff and training